## Sheet1
When: 28/05/2022 14:00 |  | Who: Daniel van Wyk | Application: Timups
ID | Scenario Title | Status | Scenario | Remarks
1 | Landing/Home Page | Pass | Follow link to website | Correct and functional landing page displayed
2 | Home Page - Buttons | Failed | Home Page buttons "Contact Us/View All/Read More/view more" tested | Buttons all Non-Functional, return to top of page
3 | Home Page - Conatct Us | Pass | Contact Form Tested | Displays error if incorrect email format entered, pressing send works.
4 | Home Page - Testimonial | Pass | Testimonials "<" ">" buttons tested | Pressing the buttons correctly scrolls through testimonials
5 | Watches Page | Pass | Watches Page navigated to by pressing "Watches" | Watches tab on Navbar correctly navigates you to the watches page NOTE: "Watches" becomes "Products" on the Navbar when on the watches page.
6 | Watches Page - Items | Failed | Watches Page items tested | Watches items cannot be viewed individually, pressing them retruns to top of page
7 | Watches Page - View All | Failed | "View All" button tested | Button non-functional, returns to top of page
8 | About Page | Pass | About Page navigated to by pressing "About" | About tab on Navbar correctly navigates you to the About page
9 | About Page - Read More | Failed | "Read More" button tested | Button non-functional, returns to top of page
10 | Contact Us Page | Pass | Contact Us Page navigated to by pressing "Contact Us" | Contact Us tab on Navbar correctly navigates you to the Contact Us page
11 | Contact Us Page - Form | Pass | Contact Form Tested | Displays error if incorrect email format entered, pressing send works.
12 | Orders Page | Pass | Orders Page navigated to by pressing "Orders" | Orders tab on Navbar correctly navigates you to the Orders page
13 | Orders Page - Buttons | Failed | Orders Page buttons "View Order/Track Shipment/Buy It Again/Requet A Return" tested | Buttons all Non-Functional, return to top of page
14 | Orders Page - Item Display | Failed | Items in shopping cart inspected | Order display shows green watch with blue color listed.
15 | Orders Page - Order Summary | Failed | Order Summary calculator math checked | $54.97+$4.30-$5.55=$53.72, total displays $53.65
16 | TIMUPS logo/Home button | Pass | TIMUPS logo/Home button tested | Buttons successfully navigate you to home